## Feature status
Project | Feature | Status
Leagleship CMS | Admin login and logout | Done
Leagleship CMS | Dashboard overview (counts + recent items) | Done
Leagleship CMS | Events: create, edit, publish, delete | Done
Leagleship CMS | Programs: create, edit, publish, delete | Done
Leagleship CMS | Manifestos: create, edit, reorder, publish, delete | Done
Leagleship CMS | Rich-text editor (TipTap) for manifesto bodies | Done
Leagleship CMS | Image uploads with in-browser resizing (no php.ini needed) | Done
Leagleship CMS | Pages: block builder (heading, paragraph, rich text, image, quote, stat) | Done
Leagleship CMS | Pages: reorder, remove, publish, delete blocks | Done
Leagleship CMS | Site settings: footer, contact, social links, newsletter copy | Done
Leagleship CMS | API /api/events (published only) | Done
Leagleship CMS | API /api/programs (published only) | Done
Leagleship CMS | API /api/manifestos (published only) | Done
Leagleship CMS | API /api/pages (blocks + rendered HTML) | Done
Leagleship CMS | API /api/site | Done
Leagleship CMS | Navy/gold Material design system with toast feedback | Done
Leagleship CMS | Test suite (61 tests), Pint style, PHPStan clean | Done
Leagleship CMS | Publish the seeded pages (Home, About, Founder, Philosophy) | Not started
Leagleship CMS | Delete stored images when events/programs/manifestos are deleted | Not started
Leagleship CMS | Newsletter signup capture | Not started
Leagleship CMS | Hero copy and impact stats editing | Not started
Leagleship CMS | SEO meta fields per page | Not started
Leagleship CMS | Media library (reuse already uploaded images) | Not started
Leagleship CMS | Revisions / version history | Not started
Leagleship CMS | Editor roles beyond the single admin | Not started
Leagleship CMS | Deploy to production | Not started